## Effort Plan
CourseGraph - Effort Plan
FH Technikum Wien - Software Engineering Project
ID | Task / Feature | Category | Priority | Estimated Hours | Assigned To | Status | Notes
Phase 1: Setup & Infrastructure
1.1 | Project Setup (Electron + React + Vite) | Setup | High | 4 | Team | Done ✓ | Initial configuration
1.2 | Git Repository & GitHub Setup | Setup | High | 2 | Team | Done ✓ | Version control
1.3 | Development Environment Setup | Setup | High | 3 | Team | Done ✓ | VS Code, Node.js, npm
1.4 | ReactFlow Integration | Setup | High | 4 | Team | Done ✓ | Graph library setup
Phase 2: Core Functionality (FR1-FR3)
2.1 | Custom Node Components | Development | High | 8 | Developer 1 | Done ✓ | LEO & Assessment nodes
2.2 | Node Create/Edit/Delete (FR1) | Development | High | 12 | Developer 1 | Done ✓ | CRUD operations
2.3 | Add Node Dialog with Type Selection | Development | High | 6 | Developer 2 | Done ✓ | User interface
2.4 | Connect Nodes (FR2) | Development | High | 10 | Developer 2 | In Progress | Drag & drop connections
2.5 | Interactive Graph Navigation (FR3) | Development | High | 8 | Developer 3 | Done ✓ | Zoom, pan, drag
2.6 | Edge Labels & Types | Development | Medium | 6 | Developer 2 | To Do | requires/implies/tests
Phase 3: Visual Design (FR4)
3.1 | Node Styling & Color Scheme | Design | High | 4 | Developer 3 | Done ✓ | Blue/Green differentiation
3.2 | Node Badges (LEO/Assessment) | Design | Medium | 3 | Developer 3 | Done ✓ | Visual indicators
3.3 | Toolbar & UI Components | Design | High | 6 | Developer 4 | Done ✓ | Modern interface
3.4 | MiniMap Styling | Design | Low | 2 | Developer 4 | Done ✓ | Overview component
3.5 | Responsive Layout | Design | Medium | 4 | Developer 4 | To Do | Different screen sizes
Phase 4: Save/Load/Export (FR5)
4.1 | Save Graph as JSON | Development | High | 8 | Developer 1 | To Do | Local file storage
4.2 | Load Graph from JSON | Development | High | 6 | Developer 1 | To Do | File parsing
4.3 | Export as PNG | Development | Medium | 10 | Developer 2 | To Do | Image generation
4.4 | Export as Excel | Development | Medium | 12 | Developer 2 | To Do | Spreadsheet export
4.5 | Auto-Save Functionality | Development | Low | 6 | Developer 1 | To Do | Periodic saving
Phase 5: Advanced Features (FR6)
5.1 | Auto-Layout Algorithm | Development | Medium | 10 | Developer 3 | To Do | Graph organization
5.2 | Reset/New Project Dialog | Development | Medium | 4 | Developer 4 | To Do | Confirmation dialogs
5.3 | Undo/Redo Functionality | Development | Low | 12 | Developer 3 | To Do | History management
5.4 | Search & Filter Nodes | Development | Low | 8 | Developer 4 | To Do | Search functionality
Phase 6: Testing & Quality Assurance
6.1 | Unit Tests (Components) | Testing | High | 10 | Developer 1 | To Do | Jest/React Testing
6.2 | Integration Tests | Testing | High | 8 | Developer 2 | To Do | Full workflow tests
6.3 | Usability Testing (NFR1) | Testing | High | 6 | Team | To Do | User acceptance
6.4 | Performance Testing (NFR2) | Testing | Medium | 4 | Developer 3 | To Do | 100+ nodes test
6.5 | Accessibility Testing (NFR4) | Testing | Medium | 4 | Developer 4 | To Do | Keyboard navigation
6.6 | Bug Fixes & Polish | Development | High | 12 | Team | To Do | Final improvements
Phase 7: Documentation & Deployment
7.1 | User Documentation | Documentation | High | 6 | Developer 4 | To Do | User guide
7.2 | Technical Documentation | Documentation | High | 8 | Developer 1 | To Do | Architecture docs
7.3 | README.md | Documentation | High | 2 | Team | Done ✓ | GitHub documentation
7.4 | Build & Package App | Deployment | High | 4 | Developer 2 | To Do | Distribution packages
7.5 | Final Presentation | Documentation | High | 8 | Team | To Do | Project presentation
Summary & Totals
Total Estimated Hours:
Tasks Completed:
Tasks In Progress:
Tasks To Do:

## Team Assignment
Team Member Allocation
Team Member | Total Hours | Completed Hours | Remaining Hours | Progress %
Developer 1 | 48 | 24 | 24 | 50%
Developer 2 | 44 | 6 | 38 | 14%
Developer 3 | 34 | 21 | 13 | 62%
Developer 4 | 34 | 15 | 19 | 44%
Team | 21 | 11 | 10 | 52%